## Sheet1
INVOICE
Invoice date: 12/12/17
Due date: 02/10/18
PRO_13_069 -Smith residence
Construction of a detached house
BARZAC
95 S. Market Street
San Jose, CA 95113
Estimated cost of work (Excl tax): $190,000.00
Provisional amount of remuneration (Excl tax): $20,900.00
Elements of missions |  | % | Pre-tax | Progress
|  |  | amount | Rate | Pre-tax amount
Preliminary design |  | 20% | 4180 | 100% | 4180
Building Permit Filing |  | 23% | 4807 | 100% | 4807
General Contractor duties |  | 15% | 3135 | 100% | 3135
Site management |  | 34% | 7106 | 46.15% | 3279.72
Inspection management |  | 8% | 1672
| Total | 100% | 20900 |  | 15401.72
|  |  |  | Total costs (excl tax): | 15401.72
|  |  |  | Previously billed amt (excl tax): | 14855.1
|  |  |  | Subtotal (excl tax): | 546.62
|  |  |  | Amount excl tax: | 546.62
|  |  |  | tax 20%: | 109.324
|  |  |  | Amount incl tax: | 655.944
|  |  |  | Direct payments to subcontractors : | 104.6
|  |  |  | Total Amount due (incl tax): | 551.344